## Logic Capacity Planning
LOGIC OF CAPACITY PLANNING - WITH ADJUSTMENT FOR LEAVES
JOB TASK TABLE
Task Details | Allocated Hours | Step 03 | Step 04 | Step 5 | Step 07 | Step 08 | Step 9 | Step 10 | Step 12 | Step 13 | Step 14 | Step 15 | Step 18 | Step 19 | Step 21 | Step 22 | Step 23 | Step 24 | Step 25
|  | Calculate Workable Days Between Start - Due Date (Minus Public Holidays / Weekends / Staff Non Workable Day of Week) | Available Workable Hrs: Multiply No. Of Workable Days into Workable Hours (Default = 8 Hrs / Day) | Calculate: Average Task Hours per Workable Day (INITIAL) | SUM all distributed Leave Hours from Step 06 | Remaining Workable Hrs: Subtract: Total Leave Hours (Step 07) from Available Workable Hours (Step 04) | Remaining Workable Days = Divide: Remaining Workable Hours by 8 (8 Hours / Day) | Average Allocated Hours for Days WITHOUT Leave | SUM all distributed Task Hours on Days WITHOUT Leave from Step 11 | Calculate Remaining Task Hours | Create a Calculated Column of Count of Days WITH Leave (Flagged in Step 02) | Average Allocated Hours for Days WITH Leave | Task Hours Worked TILL YESTERDAY (Taken from Time Sheet) | Task Hrs Remaining | Sum of Task Hours Allocated during "Days with Leave" Between Today & Due Date | Task Hrs Remaining after adjusting for Days WITH Leave | Count of Remanining Days WITHOUT Leave | Allocated Avg Task Hrs per Remaining Days WITHOUT Leave | FLAG: Task Can be Completed within Due Date?
Work Task | 65 | 40 | 320 | 1.625 | 25 | 295 | 36.875 | 1.7627 | 0 | 65 | 40 | 1.625 | 1 | 64 | 55.25 | 8.75 | 0 | 0 | FALSE
Leave | 25 | Step 03: 40; Step 04: 320; Step 5: 0.625
(Suppose - Leave Starts Date = 23 Dec 2020 and End Date = 30 Mar 2021 ) |  | Step 25: IF Step 24 > 8 Hrs OR IS NULL
Total of STAFF TASK ALLOCATION TABLE (Below) |  | Step 04: 40; Step 5: 40; Step 07: 25; Step 08: 0; Step 9: 65; Step 10: 65; Step 12: 55.25; Step 13: 0; Step 14: 55.25
THE TOTAL AT THIS STEP WOULD MATCH THE ALLOCATED HRS OF THE TASK (65 Hours)
STAFF - TASK - ALLOCATION TABLE | bar: Step 03 to Step 14
Date | Day | Step 03: Step 01; Step 5: Step 02; Step 07: Step 06; Step 08: Step 11; Step 9: Step 16; Step 10: Step 17; Step 12: Step 20; Step 13: Step 25; Step 14: Step 26
|  | Flag: Public Holidays, Weekends and Staff Non Workable Day of the Week | Count of Workable Days | Flag Leave Date Range between Task | Allocate Avg. Task Hours for Leaves (Initial) for Days WITH Leave | Allocate Avg Task Hours calculated in Step 10 for Days WITHOUT LEAVE | Allocate Avg Task Hours calculated in Step 10 for Days WITH LEAVE | Combine Avg Allocated Task Hrs for Days WITH Leave (Step 16) and Days WITHOUT Leave (Step 11) | Task Hours Allocated during "Days with Leave" Between Today & Due Date | Allocated Avg Task Hrs per Remaining Days WITHOUT Leave | Total Revised Aloocated Remaing Task Hrs between Today and Due Date
2020-12-23 | Wed | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625
2020-12-24 | Thu | Step 03: Carl Not Working
2020-12-31 | Thu | Step 03: Carl Not Working
2020-12-26 | Sat | Step 03: Weekend
2020-12-27 | Sun | Step 03: Weekend
2020-12-28 | Mon | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625
2020-12-29 | Tue | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625
2020-12-30 | Wed | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625
2021-01-07 | Thu | Step 03: Carl Not Working
2021-01-08 | Fri | Step 03: Carl Not Working
2021-01-02 | Sat | Step 03: Weekend
2021-01-03 | Sun | Step 03: Weekend
2021-01-04 | Mon | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625
2021-01-05 | Tue | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625
2021-01-06 | Wed | Step 03: Public Holiday
2021-01-14 | Thu | Step 03: Carl Not Working
2021-01-15 | Fri | Step 03: Carl Not Working
2021-01-09 | Sat | Step 03: Weekend
2021-01-10 | Sun | Step 03: Weekend
2021-01-11 | Mon | Step 03: TODAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-01-12 | Tue | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-01-13 | Wed | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-01-21 | Thu | Step 03: Carl Not Working; Step 12: 0; Step 14: 0
2021-01-22 | Fri | Step 03: Carl Not Working; Step 12: 0; Step 14: 0
2021-01-16 | Sat | Step 03: Weekend; Step 12: 0; Step 14: 0
2021-01-17 | Sun | Step 03: Weekend; Step 12: 0; Step 14: 0
2021-01-18 | Mon | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-01-19 | Tue | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-01-20 | Wed | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-01-28 | Thu | Step 03: Carl Not Working; Step 12: 0; Step 14: 0
2021-01-29 | Fri | Step 03: Carl Not Working; Step 12: 0; Step 14: 0
2021-01-23 | Sat | Step 03: Weekend; Step 12: 0; Step 14: 0
2021-01-24 | Sun | Step 03: Weekend; Step 12: 0; Step 14: 0
2021-01-25 | Mon | Step 03: Public Holiday; Step 12: 0; Step 14: 0
2021-01-26 | Tue | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-01-27 | Wed | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-02-04 | Thu | Step 03: Carl Not Working; Step 12: 0; Step 14: 0
2021-02-05 | Fri | Step 03: Carl Not Working; Step 12: 0; Step 14: 0
2021-01-30 | Sat | Step 03: Weekend; Step 12: 0; Step 14: 0
2021-01-31 | Sun | Step 03: Weekend; Step 12: 0; Step 14: 0
2021-02-01 | Mon | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-02-02 | Tue | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-02-03 | Wed | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-02-11 | Thu | Step 03: Carl Not Working; Step 12: 0; Step 14: 0
2021-02-12 | Fri | Step 03: Carl Not Working; Step 12: 0; Step 14: 0
2021-02-06 | Sat | Step 03: Weekend; Step 12: 0; Step 14: 0
2021-02-07 | Sun | Step 03: Weekend; Step 12: 0; Step 14: 0
2021-02-08 | Mon | Step 03: Public Holiday; Step 12: 0; Step 14: 0
2021-02-09 | Tue | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-02-10 | Wed | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-02-18 | Thu | Step 03: Carl Not Working; Step 12: 0; Step 14: 0
2021-02-19 | Fri | Step 03: Carl Not Working; Step 12: 0; Step 14: 0
2021-02-13 | Sat | Step 03: Weekend; Step 12: 0; Step 14: 0
2021-02-14 | Sun | Step 03: Weekend; Step 12: 0; Step 14: 0
2021-02-15 | Mon | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-02-16 | Tue | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-02-17 | Wed | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-02-25 | Thu | Step 03: Carl Not Working; Step 12: 0; Step 14: 0
2021-02-26 | Fri | Step 03: Carl Not Working; Step 12: 0; Step 14: 0
2021-02-20 | Sat | Step 03: Weekend; Step 12: 0; Step 14: 0
2021-02-21 | Sun | Step 03: Weekend; Step 12: 0; Step 14: 0
2021-02-22 | Mon | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-02-23 | Tue | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-02-24 | Wed | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-03-04 | Thu | Step 03: Carl Not Working; Step 12: 0; Step 14: 0
2021-03-05 | Fri | Step 03: Carl Not Working; Step 12: 0; Step 14: 0
2021-02-27 | Sat | Step 03: Weekend; Step 12: 0; Step 14: 0
2021-02-28 | Sun | Step 03: Weekend; Step 12: 0; Step 14: 0
2021-03-01 | Mon | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-03-02 | Tue | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-03-03 | Wed | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-03-11 | Thu | Step 03: Carl Not Working; Step 12: 0; Step 14: 0
2021-03-12 | Fri | Step 03: Carl Not Working; Step 12: 0; Step 14: 0
2021-03-06 | Sat | Step 03: Weekend; Step 12: 0; Step 14: 0
2021-03-07 | Sun | Step 03: Weekend; Step 12: 0; Step 14: 0
2021-03-08 | Mon | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-03-09 | Tue | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-03-10 | Wed | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-03-18 | Thu | Step 03: Carl Not Working; Step 12: 0; Step 14: 0
2021-03-19 | Fri | Step 03: Carl Not Working; Step 12: 0; Step 14: 0
2021-03-13 | Sat | Step 03: Weekend; Step 12: 0; Step 14: 0
2021-03-14 | Sun | Step 03: Weekend; Step 12: 0; Step 14: 0
2021-03-15 | Mon | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-03-16 | Tue | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-03-17 | Wed | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-03-25 | Thu | Step 03: Carl Not Working; Step 12: 0; Step 14: 0
2021-03-26 | Fri | Step 03: Carl Not Working; Step 12: 0; Step 14: 0
2021-03-20 | Sat | Step 03: Weekend; Step 12: 0; Step 14: 0
2021-03-21 | Sun | Step 03: Weekend; Step 12: 0; Step 14: 0
2021-03-22 | Mon | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-03-23 | Tue | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-03-24 | Wed | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2020-12-25 | Fri | Step 03: Public Holiday; Step 14: 0
2021-01-01 | Fri | Step 03: Public Holiday; Step 14: 0
2021-03-27 | Sat | Step 03: Weekend; Step 14: 0
2021-03-28 | Sun | Step 03: Weekend; Step 14: 0
2021-03-29 | Mon | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-03-30 | Tue | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
2021-03-31 | Wed | Step 03: WORKDAY; Step 04: 1; Step 5: 1; Step 07: 0.625; Step 9: 1.625; Step 10: 1.625; Step 12: 1.625; Step 14: 1.625
Total |  | Step 04: 40; Step 5: 40; Step 07: 25; Step 08: 0; Step 9: 65; Step 10: 65; Step 12: 55.25; Step 13: 0; Step 14: 55.25